FORWARD DEPLOYED AI ENGINEERING

Capstone Project

# Stage Four: Sprint Plan

Gurunanje Wodeyar | September 2026

Version 2.0 — Updated with actual progress through Day 2

# Section 1: Your Capacity

I am working alone on this project. My realistic daily availability is 6–8 hours on weekdays and 8–10 hours on weekends. This capstone is my sole focus until the September 13 deadline.

Self-management rule: Anything blocking me for more than 1 hour gets written down, worked around, or escalated. I check the blockers list at the end of each day.

| Week / Period | Hours available | Other commitments | Days unavailable |
| --- | --- | --- | --- |
| Week 1 (completed) | ~40 hrs | None | None |
| Week 2 (Sep 7–13) | ~50 hrs | None — full focus | None |

Actual hours through Day 2: ~26 hours spent (Day 1: ~10h, Day 2: ~16h). Remaining capacity: ~24 hours across 5 days.

# Section 2: The Backlog (Updated)

All items updated with actual status and hours spent. Items originally estimated at 45 hours are tracking at ~38 hours actual for completed work — we are ahead of schedule on build tasks.

| ID | Item | Est. | Actual | Pri | Status |
| --- | --- | --- | --- | --- | --- |
| B-01 | Environment and dependency setup | 2 | 2 | P1 | DONE (Sep 5) |
| B-02 | Data loading and normalisation (Ingest) | 4 | 4 | P1 | DONE (Sep 6) |
| B-06 | Intent and urgency classifier | 6 | 8 | P1 | DONE (Sep 7, refined Sep 8) |
| B-03 | Document chunking and embedding | 4 | 3 | P1 | DONE (Sep 7) |
| B-04 | Vector store and retrieval (Retrieve) | 4 | 3 | P1 | DONE (Sep 7) |
| B-07 | Routing logic and thresholds | 3 | 2 | P1 | DONE (Sep 7) |
| B-05 | Evaluation harness (CLI) | 5 | 5 | P1 | DONE (Sep 8) |
| B-08 | Answer generation with citations | 5 | 4 | P1 | DONE (Sep 7) |
| B-09 | Guardrails and validation | 4 | 3 | P1 | DONE (Sep 7) |
| B-10 | Decision logging (SQLite) | 3 | 2 | P1 | DONE (Sep 7) |
| B-11 | First full unattended run (THE GATE) | 4 | — | P1 | IN PROGRESS — 50-ticket run scheduled Sep 9 |
| B-12 | Monitoring and dashboards | 2 | 2 | P2 | DONE (Sep 8) — Streamlit dashboard + metrics CLI |
| B-13 | CI pipeline (GitHub Actions) | 2 | — | P2 | PENDING |
| B-14 | Fairness audit | 3 | — | P2 | PENDING |
| B-15 | Report, video, and submission | 6 | — | P1 | PENDING |

Effort summary: 38 hours spent on 12 completed items vs 45 hours estimated. 7 hours saved. Remaining: B-11 (4h) + B-13 (2h) + B-14 (3h) + B-15 (6h) = 15 hours against ~24 hours capacity. Buffer: ~9 hours.

# Section 3: Actual Build Progress (Days 1–2)

The build is significantly ahead of the original plan. Days 1–2 completed work originally planned for Days 1–4.

## Day 1 (Sep 7) — Planned vs Actual

Planned: B-03 (chunking), B-04 (retrieval), B-07 (routing). Estimated: 11 hours.

Actual: Completed B-03, B-04, B-07 PLUS B-08 (generation), B-09 (guardrails), B-10 (decision logging). Six modules in one day. The full pipeline ran end-to-end for the first time. ~10 hours.

Key insight: Building all six modules in sequence while the architecture was fresh reduced context-switching overhead significantly.

## Day 2 (Sep 8) — Planned vs Actual

Planned: B-05 (evaluation harness), B-08 (generation). Estimated: 16–20 hours across Days 2–3.

Actual: Completed B-05 (evaluation harness) and made major classifier improvements:

1. Fixed pipeline order to match HLD design — Classify → Retrieve, not Retrieve → Classify. The classifier now works standalone without retrieval context, matching the architecture specification.

2. Added intent-level answerable heuristics derived from ground truth analysis: three tiers (always-false, almost-always-true, mixed) with a procedure-vs-mystery decision framework.

3. Fixed compliance_request vs data_export disambiguation — if the REASON is audit/compliance, it's compliance_request regardless of the action.

4. Built B-12 monitoring: metrics collector CLI + Streamlit dashboard with per-intent accuracy, routing distribution, guardrail pass rates, error analysis, and run comparison.

5. Created COMMANDS.md reference and Stage 3 Prompt Library v2.

Test results after Day 2 improvements: 5/5 intent accuracy, 5/5 answerable accuracy, 5/5 route accuracy on test batch.

Blocker discovered: Groq free-tier daily token limit (200K TPD) caps runs at ~50–100 tickets per day. The 20-ticket run hit this ceiling. Workaround: batch evaluation across days.

# Section 4: Revised Schedule (Days 3–7)

The original plan targeted THE GATE on Day 4. We are repositioning to Day 3 (50-ticket run) with the full 500-ticket run batched across Days 3–5 due to rate limits.

| Day | Tasks | Hours | Risk |
| --- | --- | --- | --- |
| Tue Sep 9 (Day 3) | 50-ticket evaluation run (morning). B-13: CI pipeline. B-14: Fairness audit. Continue batched 500-ticket run. | 8–10 | Rate limits |
| Wed Sep 10 (Day 4) | Continue/complete 500-ticket run. Debug failures. Analyze results with monitoring dashboard. | 6–8 | Low |
| Thu Sep 11 (Day 5) | B-15: Start written report. Stage 4 and 5 final versions. | 6–8 | Low |
| Fri Sep 12 (Day 6) | B-15: Complete report (20–30 pages). Finalize all workbooks and effort log. | 8–10 | Medium |
| Sat Sep 13 (Day 7) | B-15: Video presentation (~20 min). Final review. SUBMIT before 23:59. | 8–10 | Video time |

# Section 5: What You Will Drop If You Run Out of Time

Same priority as v1. B-12 (monitoring) is now DONE, so it is no longer on the cut list. Updated cut order:

| Item | Cut order | Status / Consequence |
| --- | --- | --- |
| B-12: Monitoring dashboards | N/A | DONE — Streamlit dashboard + metrics CLI. No longer at risk. |
| B-13: CI pipeline | 1st to go | Tests run locally. Document test suite in report. Describe intended workflow. |
| B-14: Fairness audit | 2nd to go | Decision log captures per-segment data. Describe methodology in report. |

Items NEVER cut: B-05 (harness), B-11 (THE GATE), B-15 (report + video + submission).

# Section 6: Daily Check-in Record

Ten minutes at the start of each day. This record feeds the effort log.

| Date | Finished since yesterday | Doing today | Blocked by |
| --- | --- | --- | --- |
| Sep 7 (Sun) Day 1 | Stages 1–3 complete (Discovery, PRD v1, Prompt Library v1). Ingest + Classify built and tested. | B-03: Doc chunking + embedding. B-04: Retrieval. B-07: Routing. B-08: Generation. B-09: Guardrails. B-10: Decision logging. | None. |
| Sep 8 (Mon) Day 2 | B-03, B-04, B-07, B-08, B-09, B-10 all completed and tested. Full pipeline runs end-to-end. 6 modules built in one day. | B-05: Evaluation harness. B-06 v2: Classifier refinement — pipeline order fix (Classify→Retrieve to match HLD), intent-level answerable heuristics, procedure-vs-mystery framework, compliance_request vs data_export disambiguation. B-12: Monitoring module + Streamlit dashboard. Stage 3 Prompt Library v2. | Groq free-tier rate limits (200K TPD) — 20-ticket run hit daily token ceiling after 6 successful tickets. 14/20 tickets failed with rate limit errors. Workaround: batch runs across days, run 50 tickets tomorrow morning after daily reset. |
| Sep 9 (Tue) Day 3 | (To be filled after today's work) | 50-ticket evaluation run. B-13: CI pipeline. B-14: Fairness audit. | (To be filled) |
| Sep 10 (Wed) Day 4 | (To be filled) | B-11: Full 500-ticket run (if rate limits allow). Debug and fix issues. | (To be filled) |
| Sep 11 (Thu) Day 5 | (To be filled) | B-15: Start written report (20–30 pages). | (To be filled) |
| Sep 12 (Fri) Day 6 | (To be filled) | B-15: Complete report. Finalize all workbooks. | (To be filled) |
| Sep 13 (Sat) Day 7 | (To be filled) | B-15: Video presentation (~20 min). Final review. SUBMIT before 23:59. | (To be filled) |