FORWARD DEPLOYED AI ENGINEERING

Capstone Project

Stage Four: Sprint Plan

CloudServe Solutions — Intelligent Support System

Prepared by: Gurunanje  Wodeyar

Date: September 7, 2026

Sprint window: September 7 – September 13, 2026 (7 days)

# 1  Section One: Your Capacity

I am working alone on this project. My realistic daily availability is 6–8 hours on weekdays and 8–10 hours on weekends. I have no other major commitments this week — this capstone is my sole focus until the September 13 deadline.

Self-management rule: Anything blocking me for more than 1 hour gets written down, worked around, or escalated (asked in the course forum or to my AI mentor). I check the blockers list at the end of each day.

| Week / Period | Hours available | Other commitments | Days unavailable |
| --- | --- | --- | --- |
| Week 1 (completed) | ~40 hrs | None | None |
| Week 2 (Sep 7–13) | ~50 hrs | None — full focus | None |
| Week 3 (N/A — deadline is Sep 13) | N/A | N/A | N/A |

Total available for build + evaluation + submission: approximately 50 hours across 7 days. This is aggressive but achievable because the discovery and requirements work is complete, the architecture is clear, and two core modules (ingest and classify) are already built and tested.

# 2  Section Two: The Backlog

Items already completed are marked with (DONE). Remaining items are estimated in hours and prioritized P1 (must have) through P3 (nice to have). The total estimated effort for remaining work is ~42 hours against ~50 hours of capacity, leaving ~8 hours of buffer for debugging and unexpected issues.

| ID | Item | Est. hrs | Priority | Depends on | Definition of done |
| --- | --- | --- | --- | --- | --- |
| B-01 | Environment and dependency setup | 2 | P1 | — | Python 3.13 venv created, all dependencies installed (langchain, chromadb, groq, pydantic, fastapi), .env configured with GROQ_API_KEY, .gitignore includes .env. DONE. |
| B-02 | Data loading and normalisation (Ingest) | 4 | P1 | B-01 | parse_ticket() accepts raw JSON, returns IngestedTicket with StandardTicket + ground truth labels. Pydantic validation catches malformed tickets. 20 unit tests passing. DONE. |
| B-06 | Intent and urgency classifier | 6 | P1 | B-02 | classify_ticket() sends StandardTicket to Groq LLM, returns ClassificationResult with intent (22 categories), urgency, answerable_from_docs, confidence scores. Pydantic validates all outputs. 86.4% intent accuracy on 22-ticket sample. DONE. |
| B-03 | Document chunking and embedding | 4 | P1 | B-02 | Load 29 CloudServe doc articles, chunk into ~500-token passages with overlap, embed using all-MiniLM-L6-v2, store in ChromaDB. Script is idempotent (rebuild from scratch). Done = chunks stored, retrieval returns relevant passages for test queries. |
| B-04 | Vector store and retrieval (Retrieve) | 4 | P1 | B-03 | retrieve_context() takes a ticket's combined_text, queries ChromaDB, returns top-k chunks with similarity scores and source article metadata. Done = retrieval returns relevant context for 5+ test tickets, precision visually confirmed. |
| B-05 | Evaluation harness | 5 | P1 | B-02 | CLI script accepting --input and --output. Loads tickets from input JSON, runs full pipeline (ingest → classify → retrieve → route → generate → validate), writes results to output JSON. Handles errors per-ticket without crashing. Done = processes all 500 dev tickets with --input data/development_tickets.json --output output.json. |
| B-07 | Routing logic and thresholds | 3 | P1 | B-06 | route_ticket() takes ClassificationResult, returns route decision (auto_respond or escalate) with reason. Rules: must_not_auto_respond=True → escalate; answerable_from_docs=False → escalate; intent_confidence < 0.80 → escalate; else → auto_respond. Done = unit tests cover all routing paths, including edge cases at threshold boundary. |
| B-08 | Answer generation with citations | 5 | P1 | B-04 | generate_response() takes ticket + retrieved context + classification, calls Groq LLM to draft a support response with inline citations to source articles. Only called for auto_respond route. Done = generates coherent responses for 5+ test tickets with verifiable citations. |
| B-09 | Guardrails and validation | 4 | P1 | B-08 | validate_response() checks generated response against guardrail rules: no hallucinated URLs, no promises of SLA, no PII in response, response addresses the ticket's actual question, citations reference real articles. Returns pass/fail with reasons. Done = catches at least 3 types of bad responses in unit tests. |
| B-10 | Decision logging | 3 | P1 | B-07 | Every pipeline decision logged to SQLite with 14-field schema (decision_id, timestamp, ticket_id, stage, prediction, confidence, alternatives, sources_used, threshold_applied, action_taken, reason, guardrail_results, prompt_version, requirement_ids). Done = full pipeline run produces queryable decision log. |
| B-11 | First full unattended run (THE GATE) | 4 | P1 | B-05, B-09 | Run evaluation harness over all 500 dev tickets unattended. System must not crash, must produce valid output JSON, must handle all edge cases. This is the acceptance test for A9. Done = clean run, output JSON has 500 entries, no crashes, no manual intervention. |
| B-12 | Monitoring and dashboards | 2 | P2 | B-10 | Prometheus metrics (request count, latency histogram, error rate, confidence distribution) exposed via FastAPI /metrics endpoint. Grafana dashboard with 4 panels. Done = dashboard screenshot shows live metrics from a test run. |
| B-13 | CI pipeline | 2 | P2 | B-11 | GitHub Actions workflow: runs unit tests on push, lints with ruff, checks no secrets in code. Done = green CI badge on main branch, workflow file committed. |
| B-14 | Fairness audit | 3 | P2 | B-11 | Analyse pipeline decisions across ticket segments (plan tier, urgency, intent). Check for systematic bias in routing or response quality. Done = fairness report with per-segment metrics, any disparities documented with explanation. |
| B-15 | Report, video, and submission package | 6 | P1 | all | 20–30 page PDF report, ~20 min video with live demo (showing escalation + guardrail trigger), effort log entries, all 5 workbooks compiled. PRD revision log (Stage 5) completed. Done = all files submitted before Sep 13 23:59. |

Effort summary:

Completed: B-01 (2h) + B-02 (4h) + B-06 (6h) = 12 hours done

Remaining: B-03 (4h) + B-04 (4h) + B-05 (5h) + B-07 (3h) + B-08 (5h) + B-09 (4h) + B-10 (3h) + B-11 (4h) + B-12 (2h) + B-13 (2h) + B-14 (3h) + B-15 (6h) = 45 hours

Capacity: ~50 hours. Buffer: ~5 hours.

# 3  Section Three: The Build Plan — Days 1–4 (Sep 7–10)

The build follows the dependency chain in the backlog. The retrieval layer and evaluation harness come early (per guidelines), because everything downstream depends on them. The unattended full run (THE GATE) is targeted for Day 4, not the last day.

| Day | What will be finished by end of day | Hours | Risk to this |
| --- | --- | --- | --- |
| Sun Sep 7 (Day 1) | B-03: Document chunking and embedding B-04: Vector store and retrieval B-07: Routing logic and thresholds | 8–10 | ChromaDB setup issues (version conflicts, embedding model download). Mitigation: pin versions, pre-download model. |
| Mon Sep 8 (Day 2) | B-05: Evaluation harness (CLI with --input/--output) B-08: Answer generation with citations (first pass) | 8–10 | Groq rate limits on free tier slow batch processing. Mitigation: add sleep between calls, implement retry with backoff. |
| Tue Sep 9 (Day 3) | B-08: Answer generation (complete + test) B-09: Guardrails and validation B-10: Decision logging (SQLite) | 8–10 | LLM response quality may need prompt iteration. Mitigation: start with simple prompt, iterate based on sample outputs. |
| Wed Sep 10 (Day 4) | B-11: FIRST FULL UNATTENDED RUN (THE GATE) Debug any failures from full run Fix edge cases discovered during run | 8–10 | This is the highest-risk day. Full run will expose issues invisible in unit tests. Mitigation: run early in the day, leave full day for fixes. |

# 4  Section Four: Polish and Submission — Days 5–7 (Sep 11–13)

By Day 5, the core pipeline should be working end-to-end and THE GATE should be passed. These final days focus on evaluation, governance artefacts, and the submission package. If the full run on Day 4 revealed critical bugs, Day 5 is the overflow day to fix them.

| Day | What will be finished by end of day | Hours | Risk to this |
| --- | --- | --- | --- |
| Thu Sep 11 (Day 5) | B-12: Monitoring dashboards (Prometheus + Grafana) B-13: CI pipeline (GitHub Actions) B-14: Fairness audit Stage 5: PRD Revision Log (required) | 8–10 | Grafana setup complexity. Mitigation: use docker-compose with pre-built dashboard JSON. If blocked, screenshot manual metrics instead. |
| Fri Sep 12 (Day 6) | B-15 (part 1): Written report (20–30 pages) Update Prompt Library with PR-02, PR-03, PR-04 Effort log compilation All workbooks finalised | 8–10 | Report writing takes longer than expected. Mitigation: use structured template, write section-by-section, do not polish until complete. |
| Sat Sep 13 (Day 7) | B-15 (part 2): Video presentation (~20 min) Live demo recording (escalation + guardrail) Final review of all submission files SUBMIT before 23:59 | 8–10 | Video recording and editing. Mitigation: record in one take with screen share, keep it simple. Submit 2 hours before deadline as buffer. |

# 5  Section Five: What You Will Drop If You Run Out of Time

Cuts are ordered to protect the highest-weighted marking criteria. Implementation (35%) and Evaluation (20%) are protected; Governance (10%) and Communication (10%) items are cut first. The core pipeline and THE GATE are never cut.

| Item | Cut order | Consequence of cutting it | What you will say about it in the report |
| --- | --- | --- | --- |
| B-12: Monitoring dashboards (Grafana) | 1st to go | Lose visual dashboards. Prometheus metrics endpoint still works. Marks impact: small — dashboards are presentation polish, not core functionality. | Document that metrics are exposed via /metrics endpoint. Show raw Prometheus output in report. Explain Grafana was planned but cut for time. |
| B-13: CI pipeline (GitHub Actions) | 2nd to go | Lose automated test runs on push. Tests still run locally. Marks impact: small — CI is operational maturity, not core AI pipeline. | Document the test suite and how to run it locally. Note CI was planned and describe the intended workflow in the report. |
| B-14: Fairness audit | 3rd to go | Lose explicit bias analysis. Decision log still captures per-segment data. Marks impact: moderate — governance carries 10% of marks. | Acknowledge the gap honestly. Show decision log data that would support a fairness analysis. Describe the intended methodology and what the audit would have checked. |

Items that are NEVER cut:

B-03/B-04 (retrieval), B-05 (evaluation harness), B-07 (routing), B-08 (generation), B-09 (guardrails), B-10 (decision logging), B-11 (THE GATE), B-15 (report + video + submission). These are core pipeline, evaluation, and submission — without them, the project fails acceptance criteria A1–A12.

# 6  Section Six: Daily Check-in Record

Ten minutes at the start of each day, answering the same three questions. This record feeds the effort log and is where blockers get noticed before they consume two days.

| Date | Finished since yesterday | Doing today | Blocked by |
| --- | --- | --- | --- |
| Sep 7 (Sun) | Stages 1–3 complete (Discovery, PRD, Prompt Library). Ingest + Classify built and tested. | B-03: Doc chunking + embedding. B-04: Retrieval. B-07: Routing logic. | None currently. |
| Sep 8 (Mon) | (To be filled) | (To be filled) | (To be filled) |
| Sep 9 (Tue) | (To be filled) | (To be filled) | (To be filled) |
| Sep 10 (Wed) | (To be filled) | (To be filled) | (To be filled) |
| Sep 11 (Thu) | (To be filled) | (To be filled) | (To be filled) |
| Sep 12 (Fri) | (To be filled) | (To be filled) | (To be filled) |
| Sep 13 (Sat) | (To be filled) | (To be filled) | (To be filled) |